## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Gather dataset for credit underwriting from Kaggle,ChatGPT and validate it | MUST HAVE | Kaggle,ChatGPT Account | Anil kumar | 3- Completed
S1 | S1 | US-002 | Perform data preprocessing steps like data cleaning, handle null values etc. | MUST HAVE | Google /Jupyter notebook/ | Anil kumar | 3- Completed
S1 | S1 | US-003 | Conduct initial exploratory data analysis (EDA) to understand trends | SHOULD HAVE | Python Libraries | Anil kumar | 3- Completed
S2 | S2 | US-001 | Perform Outlier removal for numerical features, Perform scaling numerical features | MUST HAVE | - | Anil kumar | 3- Completed
S2 | S2 | US-002 | Data encoding for categorical features | MUST HAVE | - | Anil kumar | 3- Completed
S3 | S3 | US-003 | models (e.g., Gradient boost, Random Forest, etc.) and evaluate performance | MUST HAVE | Scikit-Learn | Anil kumar | 3- Completed
S3 | S3 | US-004 | Identify best-performing model based on evaluation metrics | MUST HAVE | - | Anil kumar | 3- Completed
S3 | S3 | US-005 | Perform fine tuning on the best-performing model | MUST HAVE | - | Anil kumar | 3- Completed
S4 | S3 | US001 | Create a prototype webpage using Streamlit to display insights and predictions | MUST HAVE | Streamlit | Anil kumar | 3- Completed
| S3 | US001 | Develop a conversational chatbot using GENAI | MUST HAVE | AI,Streamlit | Anil kumar | 3- Completed
| S4 | US-006 | Prepare final model for deployment | MUST HAVE | streamlit libraries | Anil kumar | 3- Completed
Note on F1: ====== ID#AAABYLGvqXM Sumeet Kumar Barua08 (2024-11-14 13:03:52) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 44 | 4 | 3 | 4 | 3.5 | 2 | 1 | 0 | 1 | 5 | 8.5 | 5.5 | 5.5 | 0 | 1
SPRINT 1 BACKLOG
US-001 | TASK-001 | Introduction to project. | 2024-12-03 | 2024-12-06 | Anil kumar | About | Completed | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | TASK-002 | Gather data related to credit analysis underwriting | 2024-12-07 | 2024-12-09 | Anil kumar | Data Gathering | Completed | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | TASK-003 | Provide a brief overview of the dataset. | 2024-12-10 | 2024-12-15 | Anil kumar | Data Analysis | Completed | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 7 | 0 | 0 | 0 | 0
US-002 | TASK-004 | Conduct basic EDA on relevant features to gain insights | 2024-12-20 | 2024-12-24 | Anil kumar | Data Mining | Completed | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0
US-003 | TASK-005 | Remove outliers manually (e.g., age and income length). | 2024-12-25 | 2024-12-29 | Anil kumar | Data Preprocessing | Completed | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0
SPRINT 2 BACKLOG
US-001 | TASK-001 | Fill missing values in numerical features. | 2024-12-30 | 2024-12-31 | Anil kumar | Statiscal method | Completed | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 1.5 | 0 | 0
US-001 | TASK-002 | Scale all numerical features. | 2025-01-01 | 2025-01-10 | Anil kumar | Normalization | Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0
US-001 | TASK-003 | Evaluate the best model | 2025-01-15 | 2025-01-17 | Anil kumar | Model Evaluation | Completed | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | TASK-004 | Create the project model | 17-1-202 | 2025-01-20 | Anil kumar | Final Model | Completed | 1.5 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 3 BACKLOG
US-001 | TASK-001 | Create a Streamlit webpage for the project. | 2025-01-20 | 2025-01-23 | - | Prototype Webpage | Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | TASK-001 | Develop a conversational chatbot logic using ai | 2025-01-23 | 2025-01-28 | - | Coding | Completed | 10 | 1 | 2 | 3 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 4 BACKLOG
US-001 | TASK-001 | Final project for Deployment | 2025-01-28 | 2025-01-30 | - | Deployment | Completed | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
Note on D2: ====== ID#AAABYLGvqXg Please enter the dates in either of these formats (2024-11-14 13:03:52) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABYLGvqXI Please enter the dates in either of these formats (2024-11-14 13:03:52) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABYLGvqXQ Sumeet Kumar Barua08 (2024-11-14 13:03:52) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABYLHdiCk Sumeet Kumar Barua08 (2024-11-14 13:03:52) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABYLGvqX4 Sumeet Kumar Barua08 (2024-11-14 13:03:52) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABYLGvqXU Sumeet Kumar Barua08 (2024-11-14 13:03:52) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABYLGvqXs Sumeet Kumar Barua08 (2024-11-14 13:03:52) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABYLHdiCs Sumeet Kumar Barua08 (2024-11-14 13:03:52) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABYLGvqXY Sumeet Kumar Barua08 (2024-11-14 13:03:52) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABYLGvqXo Sumeet Kumar Barua08 (2024-11-14 13:03:52) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABYLGvqXw Sumeet Kumar Barua08 (2024-11-14 13:03:52) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABYLGvqX8 Sumeet Kumar Barua08 (2024-11-14 13:03:52) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABYLGvqXE Sumeet Kumar Barua08 (2024-11-14 13:03:52) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABYLGvqXc Sumeet Kumar Barua08 (2024-11-14 13:03:52) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABYLHdiCo Sumeet Kumar Barua08 (2024-11-14 13:03:52) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABYLGvqX0 Sumeet Kumar Barua08 (2024-11-14 13:03:52) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABYLGvqXk Sumeet Kumar Barua08 (2024-11-14 13:03:52) Pending effort hours after completion of day 14 work

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | S1 | 2024-12-03 | 2024-12-16 | Anil kumar | Exploring Drive links for self study | Time waste in Coding | Regular coding | Focused on Knowledge
2 | S2 | 2024-12-16 | 2024-12-24 | Anil kumar | Implementing advanced preprocessing | Skipping daily coding task | Experimenting | Enhanced preprocessing techniques
3 | S3 | 2024-12-25 | 2025-01-10 | Anil kumar | Regularly commit Changes in model | Procastinating | Maintaining Workflow | Developing Coding Skiils
4 | S4 | 2025-01-12 | 2025-01-20 | Anil kumar | Deployment process knowing for GIT |  |  | Improved version control and Gained familiarity with tools
5
6
7

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
S1 | Day 1 | Introducing to the springboard batch and about mentor | General Queries
S2 | Day 2 | Introducing the Project Theme | A detailed explanation given by mentor
S2 | Day 10 | Conversations on AI Real Life applications | Conducted a session and reviewed the project requirements and implementations
S3 | Day 15 | Confusion on project processing | Conducted additional research and explained the code
S4 | Day 27 | Query on predicting loan | Conducted a detailed discussion with mentor
S5 | Day 33 | Doubt in the Implementation | Mentor explained very well and resolved
S6 | Day 35 | Query on algorithms | Conducted a detailed discussion with mentor
S7 | Day 40 | Query on the final project | Provided solutions for the issue and explained the
S8 | Day 44 | Agile template confusion | Conducted a meeting where all doubts were clarified by the mentor.
S7 | Day 50 | Getting some logical error in Chatbot code in project | Resolved via meeting
S9 | Day 55 | PPT implementation | Resolved via meeting